## Slide 1
AIM FY17
CogX– Executive Status Update
12 December 2017
Cogx

## Slide 2
Cogx –Executive summary
Functional demonstration for Business Use of form upload, processing and review
Overall navigation and UI framework
NiFi pipeline implementation
Data extraction through OCR
Custom processor development
Intake workflow
Provider intake solution in the dedicated environment
Full multi-input support (API, email, ftp/S3)
Configuring solution with CSF form
Configuring solution with email and attachment
Data validation with provider specific corpus
Setting up Deloitte open cloud environment
GXP compliance
Claims intake solution in the dedicated environment
Configuring solution with CMS 1500 form
Data validation with claims specific corpus
Setting up Deloitte open cloud environment
GXP compliance
Ability to process digital and image files containing structured/ unstructured data ingested through multiple sources
OMR extraction
Applying NLP intent/entity extraction
Email listener configuration
Extraction of data from digital pdf
Deloitte Data X-Ray: Extraction of data from word and excel files
Ability to generate the configuration file for new forms from the UI console
Form templating UI
Full realization of feedback and learning loop
User Roles and permissions
Key design areas around Security and API
DevOps
Vendor assessment of XPMS for GXP validation
Multi tenancy support
Platform
CogX
Provider
CogX is a platform that enables extraction of structured, semi-structured & unstructured data and NLP services for intent, entity and attribute extraction
It has highly modular and configurable architecture
It’s platform that can be leveraged to build solutions on a need basis
R1 and R2 focus is to build platform capabilities
Separate teams have been identified at R3 for platform and solutions
Provider and claims intake solutions to be ready by the end of R3
Adverse event processing is the next solution to be built
Release 1 |  | Release 2 |  | Release 3 |  | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC
Claims
Solution
Key Activities | Risks | Mitigation
R3 Sprint#14 in progress Improved form templating, handling bundled forms, multi tenancy support, user management Provider and Claims Solution development activities | Access to more testing data to make the platform capability comparable to commercially available products Lots of traction in market and MVP for platform/ solution is yet to be released | Development will be done with a single sample form and UAT will be done with real data Focusing only on Provider, Claim and AE solution for now
Core Team
Aditya Kudumala | Sandeep Sharma | Rajinder Sobti | Nirav Mehta | Shavin Shahnawaz | Abhilash Nair | Prashanth (XPMS) | Praneeth (XPMS)
Solution

## Slide 3
Detailed Sprint Status Update
R3 Sprint#14

## Slide 4
Plan for next 2 weeks
Accomplishments
CogX Platform and Solution Status | R3 Sprint#14
Project Summary :
Sprint #14 in progress
Major functionalities planned
  Platform - UI based templating enhancement, Pipeline for digital documents, Multi-tenancy support, Enable user management, Handling bundled forms
  Solution - Provider intake requirement detailing, Review panel for digital pdf documents
GXP compliance - Meetings with XPMS for vendor assessment
Open Cloud infra - Requirements shared, awaiting estimates
Issues/ Path Forward :
Major Development Activities:
Enable new full field selection on templating with improved user experience
Enable user management on COGX
Enable Muti tenent support on COGX
Enable document service configuration from Console for data extraction
Activities Completed :
Document templating UI v0.4 – enabling full field selection, document classifier, skew correction
Table extraction capability
Domain object uploading for NLP
Document review panel for email and digital documents (word, excel and csv)
Provider solution complete field extraction
Risks | Mitigation
XPMS environment not yet stable with constant design changes | Working on independent tasks that could utilize the resources
Core Team
Aditya Kudumala | Sandeep Sharma | Rajinder Sobti | Nirav Mehta | Shavin Shahnawaz | Abhilash Nair | Prashanth (XPMS) | Praneeth (XPMS)