## Slide 1
AIM FY17
CogX Release 3 – Status Update
November 2017
Cogx

## Slide 2
Plan for next 2 weeks
Release 1 (Completed):
Functional demonstration for Business Use of form upload, processing and review
Overall navigation and UI framework
NiFi pipeline implementation
Custom processor development
Intake workflow
Release 2 (Completed):
Ability to intelligently process digital and image files containing both structured and unstructured content delivered through a variety of inputs including email
Complete OMR
Applying NLP to file intake and intent extraction
Email listener configuration
Key design areas around Security and API
Release 3 (In Progress):
Integration with case management systems and hardening of the platform
Solutions Engineer console
Full realization of feedback and learning loop
Full multi-input support (API, email, ftp/S3)
Output API development
Form templating UI
User Roles and permissions
CogX Platform
Provider Solution
Porting over the existing code for the provider solution from platform to the new dedicated environment completed. Stabilization testing in progress.
Performance testing (OCR/NLP accuracy and processing time) of the solution environment in progress
Modifications required in API Gateway and RabbitMQ integration for the solution being carried out
Completed the creation of a new solution specific domain schema
Claim Intake Solution
Porting over the existing code for the claim intake solution from platform to the new dedicated environment in progress
Performance testing (OCR, OMR and processing time) of the solution environment to be done
Modifications required in API Gateway and RabbitMQ integration for the solution being carried out
Ability to handle multi page receipt item being assessed
Risks | Mitigation
Deloitte solution environments are not yet ready | Planning to develop in XPMS environment
XPMS environment not yet stable with constant design changes | Documentation of platform design captured on Confluence
Key Activities

## Slide 3
 | 2017 |  |  |  |  |  | 
 | JUN | JUL | AUG | SEP | OCT | NOV | DEC
CogX Platform |  |  |  |  |  |  | 
Provider Solution | Porting over the existing code for the provider solution from platform to the new dedicated environment completed. Stabilization testing in progress. Performance testing (OCR/NLP accuracy and processing time) of the solution environment in progress Modifications required in API Gateway and RabbitMQ integration for the solution being carried out Completed the creation of a new solution specific domain schema |  |  |  |  |  | 
Claims Intake Solution | Porting over the existing code for the claim intake solution from platform to the new dedicated environment in progress Performance testing (OCR, OMR and processing time) of the solution environment to be done Modifications required in API Gateway and RabbitMQ integration for the solution being carried out Ability to handle multi page receipt item being assessed |  |  |  |  |  | 
12/15
7/21
Release 1
9/15
Release 2
Release 3
Functional demonstration for Business Use of form upload, processing and review
Overall navigation and UI framework
NiFi pipeline implementation
Custom processor development
Intake workflow
Capabilities Delivered
Ability to intelligently process digital and image files containing both structured and unstructured content delivered through a variety of inputs including email
Complete OMR
Applying NLP to file intake and intent extraction
Email listener configuration
Key design areas around Security and API
Capabilities Delivered
Integration with case management systems and hardening of the platform
Solutions Engineer console
Full realization of feedback and learning loop
Full multi-input support (API, email, ftp/S3)
Form templating UI
User Roles and permissions
Capabilities Planned
Risks | Mitigation
Deloitte solution environments are not yet ready | Planning to develop in XPMS environment
XPMS environment not yet stable with constant design changes | Documentation of platform design captured on Confluence